## Assumptions
assumption_key | category | lens | value_low | value_base | value_high | unit | source_url | source_type | reviewed_at | owner | notes
build_start_date | timeline | all | 2025-12-02 | 2025-12-02 | 2025-12-02 | date | /Users/olubusayoadewale/rentnow/docs/product/BUILD_COST_BASELINE_REPORT_2026-03-21.md | repo_doc | 2026-03-21 | Codex | Fixed build start date for the baseline model.
baseline_snapshot_date | timeline | all | 2026-03-21 | 2026-03-21 | 2026-03-21 | date | /Users/olubusayoadewale/rentnow/docs/product/BUILD_COST_BASELINE_REPORT_2026-03-21.md | repo_doc | 2026-03-21 | Codex | Snapshot date for the seeded baseline workbook.
person_days_per_week | model | all | 5 | 5 | 5 | days | /Users/olubusayoadewale/rentnow/docs/product/BUILD_COST_VALUATION_METHOD.md | repo_doc | 2026-03-21 | Codex | Model converts person-weeks to person-days using a 5 billable day week.
lean_blended_day_rate | rate | lean / low-cost | 285 | 310 | 353 | GBP/day | https://www.morganmckinley.com/uk/salary-guide/technology/contract-salaries | market_anchor | 2026-03-21 | Codex | Blended rate tuned to match the documented lean range across 600 to 850 person-days.
mixed_blended_day_rate | rate | realistic mixed-seniority | 535 | 565 | 612 | GBP/day | https://www.contractoruk.com/market_rates | market_anchor | 2026-03-21 | Codex | Most believable central lens. Base rate aligns with the ~£410,000 working figure.
agency_blended_day_rate | rate | premium / agency | 867 | 960 | 1118 | GBP/day | https://www.reed.com/tools/technology-salary-guide-2026 | market_anchor | 2026-03-21 | Codex | Agency-equivalent blended delivery rate including margin and delivery overhead.
lean_monthly_continuation | continuation | lean / low-cost | 18000 | 24000 | 30000 | GBP/month | /Users/olubusayoadewale/rentnow/docs/product/BUILD_COST_BASELINE_REPORT_2026-03-21.md | repo_doc | 2026-03-21 | Codex | Lean retained specialist continuation range.
mixed_monthly_continuation | continuation | realistic mixed-seniority | 35000 | 50000 | 65000 | GBP/month | /Users/olubusayoadewale/rentnow/docs/product/BUILD_COST_BASELINE_REPORT_2026-03-21.md | repo_doc | 2026-03-21 | Codex | Product-team continuation range.
agency_monthly_continuation | continuation | premium / agency | 70000 | 105000 | 140000 | GBP/month | /Users/olubusayoadewale/rentnow/docs/product/BUILD_COST_BASELINE_REPORT_2026-03-21.md | repo_doc | 2026-03-21 | Codex | Serious agency or retained squad continuation range.
central_working_figure | valuation | realistic mixed-seniority | 410000 | 410000 | 410000 | GBP | /Users/olubusayoadewale/rentnow/docs/product/BUILD_COST_BASELINE_REPORT_2026-03-21.md | repo_doc | 2026-03-21 | Codex | Documented central working figure for stakeholder use.
lean_total_range | valuation | lean / low-cost | 170000 | 224750 | 300000 | GBP | /Users/olubusayoadewale/rentnow/docs/product/BUILD_COST_BASELINE_REPORT_2026-03-21.md | repo_doc | 2026-03-21 | Codex | Seeded workbook totals should remain inside the documented lean range.
mixed_total_range | valuation | realistic mixed-seniority | 320000 | 410000 | 520000 | GBP | /Users/olubusayoadewale/rentnow/docs/product/BUILD_COST_BASELINE_REPORT_2026-03-21.md | repo_doc | 2026-03-21 | Codex | Seeded workbook totals should remain inside the documented mixed range.
agency_total_range | valuation | premium / agency | 520000 | 696000 | 950000 | GBP | /Users/olubusayoadewale/rentnow/docs/product/BUILD_COST_BASELINE_REPORT_2026-03-21.md | repo_doc | 2026-03-21 | Codex | Seeded workbook totals should remain inside the documented agency range.
Note on H2: /Users/olubusayoadewale/rentnow/docs/product/BUILD_COST_BASELINE_REPORT_2026-03-21.md
Note on H3: /Users/olubusayoadewale/rentnow/docs/product/BUILD_COST_BASELINE_REPORT_2026-03-21.md
Note on H4: /Users/olubusayoadewale/rentnow/docs/product/BUILD_COST_VALUATION_METHOD.md
Note on H5: https://www.morganmckinley.com/uk/salary-guide/technology/contract-salaries
Note on H6: https://www.contractoruk.com/market_rates
Note on H7: https://www.reed.com/tools/technology-salary-guide-2026
Note on H8: /Users/olubusayoadewale/rentnow/docs/product/BUILD_COST_BASELINE_REPORT_2026-03-21.md
Note on H9: /Users/olubusayoadewale/rentnow/docs/product/BUILD_COST_BASELINE_REPORT_2026-03-21.md
Note on H10: /Users/olubusayoadewale/rentnow/docs/product/BUILD_COST_BASELINE_REPORT_2026-03-21.md
Note on H11: /Users/olubusayoadewale/rentnow/docs/product/BUILD_COST_BASELINE_REPORT_2026-03-21.md
Note on H12: /Users/olubusayoadewale/rentnow/docs/product/BUILD_COST_BASELINE_REPORT_2026-03-21.md
Note on H13: /Users/olubusayoadewale/rentnow/docs/product/BUILD_COST_BASELINE_REPORT_2026-03-21.md
Note on H14: /Users/olubusayoadewale/rentnow/docs/product/BUILD_COST_BASELINE_REPORT_2026-03-21.md

## Baseline Valuation
snapshot_date | build_start_date | build_end_date | workstream | evidence_summary | confidence | person_weeks_low | person_weeks_base | person_weeks_high | lean_cost_low | lean_cost_base | lean_cost_high | mixed_cost_low | mixed_cost_base | mixed_cost_high | agency_cost_low | agency_cost_base | agency_cost_high | notes
2026-03-21 | 2025-12-02 | 2026-03-21 | Marketplace, search, discovery, and engagement | Explore, explore-v2, explore-labs, home, rails, saved, collections, trust cues, and conversion analytics. | Medium | 22 |  | 30 | [9 empty] | Seeded from the 2026-03-21 baseline report workstream ranges.
2026-03-21 | 2025-12-02 | 2026-03-21 | Listings, host workflows, listing quality, and media | Listing create/edit/submit, quality guidance, demo controls, image/video delivery, and host properties manager. | High | 18 |  | 24 | [9 empty] | Seeded from the 2026-03-21 baseline report workstream ranges.
2026-03-21 | 2025-12-02 | 2026-03-21 | Property Requests demand workflow | Tenant request creation, responder matching, admin registry, lifecycle management, telemetry, and notifications. | High | 10 |  | 14 | [9 empty] | Seeded from the 2026-03-21 baseline report workstream ranges.
2026-03-21 | 2025-12-02 | 2026-03-21 | Admin tooling, support, analytics, and operator surfaces | Review desk, support inbox, analytics, diagnostics, settings, and operator-facing admin workflows. | High | 18 |  | 26 | [9 empty] | Seeded from the 2026-03-21 baseline report workstream ranges.
2026-03-21 | 2025-12-02 | 2026-03-21 | Billing, payments, monetisation, and cutover preparation | Subscriptions, PAYG lanes, provider routing, reconcile flows, featured payments, and cutover readiness. | High | 14 |  | 20 | [9 empty] | Seeded from the 2026-03-21 baseline report workstream ranges.
2026-03-21 | 2025-12-02 | 2026-03-21 | Shortlets product lane | Shortlet discovery, map/filter UX, bookings, checkout, payments, reminders, trips, and host ops. | Medium | 20 |  | 28 | [9 empty] | Seeded from the 2026-03-21 baseline report workstream ranges.
2026-03-21 | 2025-12-02 | 2026-03-21 | Docs, help, training, and admin runbooks | Role help docs, admin runbooks, audit documents, and update-note discipline. | High | 6 |  | 10 | [9 empty] | Seeded from the 2026-03-21 baseline report workstream ranges.
2026-03-21 | 2025-12-02 | 2026-03-21 | Stability, release gates, PWA, CI, migrations, and automation ops | Go-live stabilization, PWA hardening, CI/release health, migration guards, and automation ops docs. | Medium | 12 |  | 18 | [9 empty] | Seeded from the 2026-03-21 baseline report workstream ranges.
|  |  | Baseline totals | Totals row sums the seeded workstream rows directly above. | [13 empty] | Central mixed base should sit near the documented ~£410,000 figure.

## Weekly Increments
week_ending | review_window_start | review_window_end | run_id | reviewer | approval_status | changed_files_count | commit_count | update_notes_count | primary_workstream | secondary_workstream | shipped_summary | evidence_refs | effort_person_days_low | effort_person_days_base | effort_person_days_high | role_mix_applied | lean_add_low | lean_add_base | lean_add_high | mixed_add_low | mixed_add_base | mixed_add_high | agency_add_low | agency_add_base | agency_add_high | confidence | next_action | notes
2026-03-28 | 2026-03-22 | 2026-03-28 | TEMPLATE-REPLACE | Reviewer name | draft | [5 empty] | Replace with the approved weekly shipped summary. | 2 to 5 evidence refs |  |  |  | mixed engineering + QA + docs | [9 empty] | Medium | review required | Template row; copy down or replace after review.

## Cumulative Totals
Build Cost Ledger v1 - cumulative view
Baseline totals |  |  |  | Central working figure
lens | baseline_low | baseline_base | baseline_high
lean / low-cost
realistic mixed-seniority |  |  |  | Build start date
premium / agency
Weekly additions to date
lens | weekly_low_total | weekly_base_total | weekly_high_total
lean / low-cost
realistic mixed-seniority
premium / agency
Current cumulative estimate
lens | cumulative_low | cumulative_base | cumulative_high
lean / low-cost
realistic mixed-seniority
premium / agency
Monthly continuation assumptions
lens | monthly_continuation_low | monthly_continuation_base | monthly_continuation_high
lean / low-cost
realistic mixed-seniority
premium / agency

## Workstream Log
week_ending | workstream | batch_title | summary | important_files | important_update_notes | impact_level | confidence | reviewer_note
2026-03-21 | Marketplace, search, discovery, and engagement | Baseline valuation snapshot | Explore, explore-v2, explore-labs, home, rails, saved, collections, trust cues, and conversion analytics. | docs/product/BUILD_COST_BASELINE_REPORT_2026-03-21.md; docs/product/ROADMAP.md | web/docs/updates/** (baseline evidence pool) | Baseline | Medium | Seed entry for the starter ledger workbook.
2026-03-21 | Listings, host workflows, listing quality, and media | Baseline valuation snapshot | Listing create/edit/submit, quality guidance, demo controls, image/video delivery, and host properties manager. | docs/product/BUILD_COST_BASELINE_REPORT_2026-03-21.md; docs/product/ROADMAP.md | web/docs/updates/** (baseline evidence pool) | Baseline | High | Seed entry for the starter ledger workbook.
2026-03-21 | Property Requests demand workflow | Baseline valuation snapshot | Tenant request creation, responder matching, admin registry, lifecycle management, telemetry, and notifications. | docs/product/BUILD_COST_BASELINE_REPORT_2026-03-21.md; docs/product/ROADMAP.md | web/docs/updates/** (baseline evidence pool) | Baseline | High | Seed entry for the starter ledger workbook.
2026-03-21 | Admin tooling, support, analytics, and operator surfaces | Baseline valuation snapshot | Review desk, support inbox, analytics, diagnostics, settings, and operator-facing admin workflows. | docs/product/BUILD_COST_BASELINE_REPORT_2026-03-21.md; docs/product/ROADMAP.md | web/docs/updates/** (baseline evidence pool) | Baseline | High | Seed entry for the starter ledger workbook.
2026-03-21 | Billing, payments, monetisation, and cutover preparation | Baseline valuation snapshot | Subscriptions, PAYG lanes, provider routing, reconcile flows, featured payments, and cutover readiness. | docs/product/BUILD_COST_BASELINE_REPORT_2026-03-21.md; docs/product/ROADMAP.md | web/docs/updates/** (baseline evidence pool) | Baseline | High | Seed entry for the starter ledger workbook.
2026-03-21 | Shortlets product lane | Baseline valuation snapshot | Shortlet discovery, map/filter UX, bookings, checkout, payments, reminders, trips, and host ops. | docs/product/BUILD_COST_BASELINE_REPORT_2026-03-21.md; docs/product/ROADMAP.md | web/docs/updates/** (baseline evidence pool) | Baseline | Medium | Seed entry for the starter ledger workbook.
2026-03-21 | Docs, help, training, and admin runbooks | Baseline valuation snapshot | Role help docs, admin runbooks, audit documents, and update-note discipline. | docs/product/BUILD_COST_BASELINE_REPORT_2026-03-21.md; docs/product/ROADMAP.md | web/docs/updates/** (baseline evidence pool) | Baseline | High | Seed entry for the starter ledger workbook.
2026-03-21 | Stability, release gates, PWA, CI, migrations, and automation ops | Baseline valuation snapshot | Go-live stabilization, PWA hardening, CI/release health, migration guards, and automation ops docs. | docs/product/BUILD_COST_BASELINE_REPORT_2026-03-21.md; docs/product/ROADMAP.md | web/docs/updates/** (baseline evidence pool) | Baseline | Medium | Seed entry for the starter ledger workbook.

## Notes & Confidence
Build Cost Ledger v1 notes and operating guidance
This workbook is a build-cost valuation model, not audited spend or business valuation.
This starter workbook uses the six-tab operating layout requested for this batch. README-style usage notes are embedded here instead of a separate README tab.
Weekly increments should stay review-based. Do not silently append approved rows without human review.
date | entry_type | lens | workstream | confidence_change | reason | owner | follow_up
2026-03-21 | model_warning | all | all | n/a | The workbook values estimate reproduction cost from repo truth and should not be presented as cash spent. | Codex | Keep stakeholder summaries explicit about the model limits.
2026-03-21 | baseline_note | realistic mixed-seniority | all | High | Central working figure is about £410,000 and should remain the default stakeholder number unless the method changes. | Codex | Review only if the methodology doc changes.
2026-03-21 | workbook_structure | all | all | Medium | Weekly Increments starts with a draft template row. Approved totals in Cumulative Totals intentionally ignore non-approved rows. | Codex | Copy the template row for each new reviewed week.